## Sheet1
| Project Start Date: | 2026-03-04 | [6 empty] | Week 1 |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4
| Project Name: | Data Seeding Script for Development Environment Deployments | [6 empty] | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-23 | 2026-03-24 | 2026-03-25
Task ID | Task Name | Start | End | Days | Depends On | Time Justification | Status | % Done
1 | Research and Analysis | 2026-03-04 | 2026-03-04 | 1 | None | Overarching task | Complete | 100% | bar: 2026-03-04
1.1 | Investigate Current Pipeline Implementation | 2026-03-04 | 2026-03-04 | 1 | None | Requires only viewing current code | Complete | 100% | bar: 2026-03-04
1.2 | Investigate Ways to Interact with Database in PowerShell | 2026-03-04 | 2026-03-04 | 1 | None | Requires looking up documentation for PowerShell libraries | Complete | 100% | bar: 2026-03-04
1.3 | Investigate Ways to Ensure Security | 2026-03-04 | 2026-03-04 | 1 | None | Requires reviewing identities used in pipeline | Complete | 100% | bar: 2026-03-04
2 | Design | 2026-03-05 | 2026-03-09 | 3 | 1 | Overarching task | Complete | 100% | bar: 2026-03-05; 2026-03-09
2.1 | Create Skeleton of Data Seeding Stage | 2026-03-05 | 2026-03-05 | 1 | 1 | Basic code stage skeleton | Complete | 100% | bar: 2026-03-05
2.2 | Create Skeleton of PowerShell Script | 2026-03-05 | 2026-03-05 | 1 | 2.1 | Basic "Hello World!" PowerShell script | Complete | 100% | bar: 2026-03-05
2.3 | Include Parameters for Activation of Data Seeding Stage | 2026-03-06 | 2026-03-06 | 1 | 2.2 | Requires gatekeeping the ability to run the to protect production environments | Complete | 100% | bar: 2026-03-06
2.4 | Add Teardown Capability to Pipelines | 2026-03-09 | 2026-03-09 | 1 | 2.3 | Requires reversing steps taken before | Complete | 100% | bar: 2026-03-09
3 | Implementation | 2026-03-10 | 2026-03-20 | 9 | 2 | Overarching task | Complete | 100% | bar: 2026-03-10; 2026-03-20
3.1 | Add Single Record to Database Through PowerShell Script | 2026-03-10 | 2026-03-11 | 2 | 2 | Requires implementing research from Task 1.2 and implementing according to schema | Complete | 100% | bar: 2026-03-10 to 2026-03-11
3.2 | Add Condition to Single Record Script to Make it Idempotent | 2026-03-12 | 2026-03-12 | 1 | 3.1 | Requires the implementation of Task 3.1 | Complete | 100% | bar: 2026-03-12
3.3 | Add Multiple Non-Attachment Records to Database Through PowerShell Script | 2026-03-13 | 2026-03-13 | 1 | 4.1 | Requires looping extension of Task 3.1 | Complete | 100% | bar: 2026-03-13
3.4 | Add Condition to Multiple Records Script to Make it Idempotent | 2026-03-13 | 2026-03-13 | 1 | 3.3 | Requires the implementation of Task 3.3 | Complete | 100% | bar: 2026-03-13
3.5 | Add Attachment Image to Repository | 2026-03-16 | 2026-03-16 | 1 | 2 | Requires adding image file, trivial | Complete | 100% | bar: 2026-03-16
3.6 | Add Record With Attachment to Database and Azure Blob Storage through PowerShell Script | 2026-03-16 | 2026-03-18 | 3 | 2, 4.2 | Requires adding file to blob storage and ensuring the steps are in the right order, potentially new security risks | Complete | 100% | bar: 2026-03-16; 2026-03-18
3.7 | Add Condition to Make Record With Attachment Script Idempotent | 2026-03-19 | 2026-03-20 | 2 | 3.6 | Requires the implementation of Task 3.6 | Complete | 100% | bar: 2026-03-19 to 2026-03-20
4 | Testing | 2026-03-12 | 2026-03-20 | 7 | 3.2 | Overarching task | Complete | 100% | bar: 2026-03-12; 2026-03-20
4.1 | Ensure Single Record Can be Displayed on Front End | 2026-03-12 | 2026-03-12 | 1 | 3.2 | Requires locally testing Task 3.2 implementation | Complete | 100% | bar: 2026-03-12
4.2 | Ensure Multiple Records Can Be Displayed on Front End | 2026-03-13 | 2026-03-13 | 1 | 3.4 | Requires locally testing Task 3.4 implementation | Complete | 100% | bar: 2026-03-13
4.3 | Ensure Record with Attachment Can Be Displayed on Front End | 2026-03-20 | 2026-03-20 | 1 | 3.7 | Requires locally testing Task 3.7 implementation | Complete | 100% | bar: 2026-03-20
5 | Documentation | 2026-03-23 | 2026-03-25 | 3 | 4 | Overarching task | Complete | 100% | bar: 2026-03-23; 2026-03-25
5.1 | Create Documentation Explaining How the Data Seeding Script Works | 2026-03-23 | 2026-03-24 | 2 | 4 | Requires thorough explanation in wiki and review by someone not working on this | Complete | 100% | bar: 2026-03-23 to 2026-03-24
5.2 | Create Documentation Explaining How to Test the Data Seeding Script | 2026-03-24 | 2026-03-25 | 2 | 4 | Requires step-by-step tutorial and review | Complete | 100% | bar: 2026-03-24 to 2026-03-25
Statuses
Not Started
In Progress
Blocked
Complete
Formulas:
Days = (NETWORKDAYS([Start],[End]))